## UTPALAA
ENVIRONMENT AND SAFETY EVALUATION
Project: |  | UTPALAA | Period | FEBRUARY |  |  | 2026
Status
Overall Score: |  | 67.03% | E.A.S.E Category: |  |  |  | BELOW AVERAGE
Topic | Sl. No. | Evaluation Elements | Status | Assessment Value | Score Applicable | Marks Obtained | Topic Percentage | Gradation
General Safety | 1 | Are Safety meetings conducted across the table at least once monthly and minutes communicated? | Yes | 3 | 3 | 3 | 52.94% | BELOW AVERAGE | [5 empty] | UTALIKA | JANUARY | 2025
| 2 | Are Safety tool-box talks conducted daily and records maintained? | Yes | 3 | 3 | 3 | [7 empty] | USSHAR | FEBRUARY | 2026
| 3 | Are Safety induction provided to all new joinings and records maintained? | Yes | 3 | 3 | 3 | [7 empty] | UTSODHARA | MARCH | 2027
| 4 | Is pre-employment medical checkup conducted for all newly joined workers? | Yes | 3 | 3 | 3 | [7 empty] | UTPALAA | APRIL | 2028
| 5 | Is work beside water bodies being conducted without any risk whatsoever? |  | NA |  | NA | [7 empty] | UDYAAT | MAY | 2029
| 6 | Are there display of Safety posters and messages in dimensions 3 feet by 4 feet? Minimum 20 numbers | Yes | 3 | 3 | 3 | [7 empty] | ESBT | JUNE | 2030
| 7 | Are there display of Safety signage and warning/ caution signs in all the relevant areas? | Yes | 3 | 3 | 3 | [7 empty] | URVISHA | JULY | 2031
| 8 | Are there display of Emergency contact numbers at prominent places in work area easily visible to the eye? | Yes | 3 | 3 | 3 | [7 empty] | THE PARK | AUGUST | 2032
| 9 | Are Near Misses reported? | No | 3 | 3 | 0 | [8 empty] | SEPTEMBER | 2033
| 10 | Are approach roads safe for vehicle and pedestrian movement? | Tending to Yes | 3 | 3 | 1.5 | [8 empty] | OCTOBER | 2034
| 11 | Are there enough resting sheds for the labours inside the work zone? | No | 3 | 3 | 0 | [8 empty] | NOVEMBER | 2035
| 12 | Are contractors served written warnings on repetitive / pending observations? | No | 3 | 3 | 0 | [8 empty] | DECEMBER | 2036
| 13 | Do the execution team members conduct safety observations (5 observations/ per day/ per person)? | No | 3 | 3 | 0 | [9 empty] | 2037
| 14 | Is percentage of rectification more than 90%? | No | 3 | 3 | 0 | [9 empty] | 2038
| 15 | Do all the unsafe jobs receive a Job Discontinuation/stoppage/penalty notice from site management? | Yes | 3 | 3 | 3 | [9 empty] | 2039
| 16 | Is the site free of High Risk (fatality potential) observations? | No | 3 | 3 | 0 | [9 empty] | 2040
| 17 | Is there minimum 1 mock drill conducted per month and the documents are available? | No | 3 | 3 | 0
| 18 | Is there minimum 1 SHE campaigns orgnised such as safety stand-downs, demonstrations, etc. per month? | Tending to Yes | 3 | 3 | 1.5
Housekeeping | 19 | Is the site neat and clean? | Tending to Yes | 4 | 4 | 2 | 45% | BELOW AVERAGE
| 20 | Are all access/ egress routes, pathways, staircases etc. free from risk of slip, trip & fall hazards | Tending to Yes | 4 | 4 | 2
| 21 | Is the site free from signs of oil spillage and other agents that can pollute the top soil? | Tending to Yes | 4 | 4 | 2
| 22 | Are walking paths for pedestrians marked and separated from vehical routes? | No | 4 | 4 | 0
| 23 | Are construction materials, earth, etc. stacked and stored that they do not roll or collapse? | Yes | 4 | 4 | 4
| 24 | Is the average illumination level of the entire project site more than equal to 150 Lux? | Tending to Yes | 4 | 4 | 2
| 25 | Are chemicals and oils stored as per recommendations in the MSDS? | No | 4 | 4 | 0
| 26 | Is the site free from rods protruding from ground or sharp objects along height of a person's face? | Tending to Yes | 4 | 4 | 2
| 27 | Are debris disposal chutes available to dispose debris from elevated floors? |  | NA |  | NA
| 28 | Is site free from water stagnation? | No | 4 | 4 | 0
| 29 | Are all job locations in the project easily approachable by all? | Yes | 4 | 4 | 4
| 30 | Is there a smoking booth available and being used? No one found smoking in the work place. | No | 4 | 4 | 0
| 31 | Is scrap/debris kept separately and safely in designated/ demarcated areas | Yes | 4 | 4 | 4
| 32 | Are deshuttered materials stacked neatly in an uncluttered manner? | Tending to Yes | 4 | 4 | 2
| 33 | Are defective materials segregated from sound materials? | Tending to No | 4 | 4 | 1
| 34 | Are Flammable materials stored separately? | Tending to Yes | 4 | 4 | 2
Personal Protective Equipment and work apparels | 35 | Is there 100% implementation of safety helmet with chin-straps? | Tending to Yes | 5 | 5 | 2.5 | 73.21% | AVERAGE
| 36 | Is there 100% implementation of safety shoes? | Tending to Yes | 5 | 5 | 2.5
| 37 | Is there 100% use of goggles ensured for chipping/ hacking jobs? | Yes | 5 | 5 | 5
| 38 | Is there 100% implementation of fluorescent jackets worn by all in the project? | Yes | 5 | 5 | 5
| 39 | Is there 100% use of suitable hand gloves for material handling? | Tending to Yes | 5 | 5 | 2.5
| 40 | Is there 100% use of ear protection in high noise zones? | Tending to Yes | NA | NA | NA
| 41 | Are use of shoulder pads for materials shifting like reinforcement implemented? | Yes | 3 | 3 | 3
Work at Height | 42 | Are all scaffolds/ staging above 6m in height, jointly checked and agreed upon by the site technical team? | Tending to Yes | 5 | 5 | 2.5 | 63.89% | AVERAGE
| 43 | Are all scaffolds and staging those are more than 6m height inspected and records available? | Yes | 5 | 5 | 5
| 44 | Are all work platforms provided with Toprails@42 inches and Midrails@21 inches? | Tending to Yes | 5 | 5 | 2.5
| 45 | Are all work platform/ gratings provided with complete gratings and secured/ tied to the scaffolding/ staging? | Tending to Yes | 5 | 5 | 2.5
| 46 | Are all floor openings, lift shafts, cut-outs, voids, slab edges, etc. protected adequately to prevent falls? | Yes | 5 | 5 | 5
| 47 | Are double layered hard barricades provided to all the shafts, balconies, slab edges, floor-to ceiling windows, etc.? | Tending to Yes | 5 | 5 | 2.5
| 48 | Are all floor openings/ floor edges / beam tops, chajjas, aisles, etc. kept free from loose materials? | Tending to Yes | 5 | 5 | 2.5
| 49 | Are safety nets, overhead protection, temporary covers for floor openings, etc free from debris accumulation? |  | NA |  | NA
| 50 | Are all areas where elevated works are in progress provided with strong overhead protection? |  | NA |  | NA
| 51 | Are safety nets provided in every alternative floors in each and every shaft? |  | NA |  | NA
| 52 | Are all lifeline ropes ( 16 mm dia.) provided for works at height where applicable? | Yes | 5 | 5 | 5
| 53 | Is use of fall arrestor and vertical lifelines implemented in all areas where frequent vertical movements are necessary? |  | NA |  | NA
| 54 | Are all mechanically operated man lifting devices (cradles and baskets) used as per guidelines? |  | NA |  | NA
| 55 | Are all work on roof carried out as per safe guidelines? |  | NA |  | NA
| 56 | Are approach ladders / paths to all work-platforms safe and defined? | Tending to No | 5 | 5 | 1.25
| 57 | Are all mobile scaffolds built as per safe guidelines? |  | NA |  | NA
| 58 | Are all mobile scaffolds used as per safe guidelines? |  | NA |  | NA
Electrical | 59 | Are all connections drawn through either 3 core or 4 core double insulated cables? | Yes | 4 | 4 | 4 | 63.89% | AVERAGE
| 60 | Is site free from defective electrical installations and accessories? | Tending to Yes | 4 | 4 | 2
| 61 | Are all electrical connections routed through RCCB (30mA rating)? | Yes | 4 | 4 | 4
| 62 | Are all RCCB inspected once a month and records maintained? | Yes | 4 | 4 | 4
| 63 | Are all above ground cables routed 7 feet above the ground from insuated hooks and clips? | Tending to Yes | 4 | 4 | 2
| 64 | Are all underground cables maintained 3 feet below the ground following IEC guidelines? | No | 4 | 4 | 0
| 65 | Is site free from cables lying along the ground? | Tending to Yes | 4 | 4 | 2
| 66 | Are all the electrical installations easily approachable? | Tending to No | 4 | 4 | 1
| 67 | Are all connections drawn with industrial type plug tops? | Yes | 4 | 4 | 4
| 68 | Is an electrical rescue kit available in the site? | Yes | 4 | 4 | 4
| 69 | Are all electrical installations and equipment earthed as per IS 3043? | Tending to Yes | 4 | 4 | 2
| 70 | Is site free from electrical malpractices? | Tending to Yes | 4 | 4 | 2
| 71 | Are all electrical installations and equipment as per IP 44 (minimum) specification? | Tending to No | 4 | 4 | 1
| 72 | Are all electricians present in the site holding valid licenses? | Yes | 4 | 4 | 4
| 73 | Are all cable joints prepared using connectors or joining kits? | Tending to Yes | 4 | 4 | 2
| 74 | Are all electrical installations provided with PCC floor and di-electric mat with appropriate voltage rating? | Yes | 4 | 4 | 4
| 75 | Are all earth pits checked on a half yearly basis and recorded? | Yes | 4 | 4 | 4
| 76 | Are suitable fire extinguisher in working condition located close to all the electrical installations? | No | 4 | 4 | 0
Welding, cutting and grinding | 77 | Are all welding machines equipped with local isolation switch? | Yes | 3 | 3 | 3 | 71.43% | AVERAGE
| 78 | Are all welding cables connected using lugs, glands and having rated return cables? | Tending to Yes | 3 | 3 | 1.5
| 79 | Are all gas welding/ cutting torches and hoses provided with flash back arrestors? | Yes | 3 | 3 | 3
| 80 | Are all welders /cutters using the right glasses/ goggles,leather apron and hand gloves? | Tending to No | 3 | 3 | 0.75
| 81 | Are all cutting hoses and welding cables free from damage and defects? | Tending to Yes | 3 | 3 | 1.5
| 82 | Do all the gas cylinders have valve guards? | Tending to Yes | 3 | 3 | 1.5
| 83 | Are all Oxygen hoses blue and DA/LPG hoses red? | Yes | 3 | 3 | 3
| 84 | Are all gas cylinders provided with double gauge pressure regulators in good condition? | Yes | 3 | 3 | 3
| 85 | Are gas cylinders stored as per laid down guidelines? | Tending to Yes | 3 | 3 | 1.5
| 86 | Are all gas cylinders transported using trolleys at all times? | Tending to No | 3 | 3 | 0.75
| 87 | Are all grinding or cutting machines provided with guards? | Tending to Yes | 3 | 3 | 1.5
| 88 | Are cutting wheels of proper RPM and specification used? | Yes | 3 | 3 | 3
| 89 | Are cutting wheels stored away from direct sunlight, moisture and other contaminants? | Yes | 3 | 3 | 3
| 90 | Are the grinding wheels stored in damp free and damage proof conditions? | Yes | 3 | 3 | 3
Vehicles, Earth movers & Lifting Equipment | 91 | Are all vehicles provided with automatic reverse horn? | Yes | 3 | 3 | 3 | 52.27% | BELOW AVERAGE
| 92 | Are all swinging equipments provided with swing alarm? | No | 3 | 3 | 0
| 93 | Are all earth moving equipments inspected periodically and findings documented? | Yes | 3 | 3 | 3
| 94 | Are all lifting equipment tested by TPLGA and the copy of certificate pasted on the equipment? | Tending to Yes | 3 | 3 | 1.5
| 95 | Are all lifting gears tested by TPLGA and the gear is colour coded? | No | 3 | 3 | 0
| 96 | Is Safe Work Load (SWL) marked on all lifting appliances? | No | 3 | 3 | 0
| 97 | Are all the lifting gears inspected periodically and findings documented? | Tending to Yes | 3 | 3 | 1.5
| 98 | Are all the lifting appliances inspected periodically and findings documented? | Tending to Yes | 3 | 3 | 1.5
| 99 | Are all the safety gadgets (limits, cut offs, indicators, preventers, accessories, etc.) available in their places? | Tending to No | 3 | 3 | 0.75
| 100 | Are all vehicles inspected periodically and findings documented? | Yes | 3 | 3 | 3
| 101 | Is the operator/ driver licensed for the device that he is operating? | Yes | 3 | 3 | 3
Fire Prevention/ Protection | 102 | Are adequate number and type of fire extinguishers available at the project site? | Tending to Yes | 5 | 5 | 2.5 | 65.62% | AVERAGE
| 103 | Are Fire fighting trainings & mock drills once in 2 months conducted periodically and documented? | Tending to Yes | 5 | 5 | 2.5
| 104 | Is the usage procedure of fire extinguisher displayed in all fire prone places? | Tending to Yes | 5 | 5 | 2.5
| 105 | Are Smoking Booths established and is being used? | Tending to Yes | 5 | 5 | 2.5
| 106 | Are fire extinguishers periodically checked and findings documented? | Yes | 5 | 5 | 5
| 107 | Are access to fire fighting aids free from obstacles? | Yes | 5 | 5 | 5
| 108 | Are fire entinguishers hung / displayed against approved yellow and black hatches? | Tending to No | 5 | 5 | 1.25
| 109 | Are all activities (thhat may lead to fire) planned and conducted keeping in mind fire prevention? | Yes | 5 | 5 | 5
First Aid & Medical Facilities | 110 | Is there a First aid room in the project site with facilities as per legal requirements? | Yes | 3 | 3 | 3 | 83.33% | GOOD
| 111 | Is Good hygiene maintained in and around the first-aid room? | Yes | 3 | 3 | 3
| 112 | Are adequate (1 for every 50) number of Qualified/ trained first-aider available at the project site? | Yes | 3 | 3 | 3
| 113 | Is a first aid register maintained in updated condition? | Yes | 3 | 3 | 3
| 114 | Is trend analysis of First Aid injuries done? | Tending to Yes | 3 | 3 | 1.5
| 115 | Is a man rescue basket / stretcher for first aid available and maintained in good condition? | Yes | 3 | 3 | 3
| 116 | Is there any tie up with local hospitals/ ambulance services and the same is documented? | No | 3 | 3 | 0
| 117 | Are sufficient number of first-aid boxes available at project site? | Yes | 3 | 3 | 3
| 118 | Is there availability of emergency vehicles at site? | Yes | 3 | 3 | 3
Welfare Facilities and labour accomodation | 119 | Are adequate number of urinals provided at every 2 floors in the work zone? |  | NA |  | NA | 96.43% | EXCELLENT
| 120 | Are provision for hygenic drinking water available in the work place? | Yes | 4 | 4 | 4
| 121 | Is pest control carried out regularly in the labour accomodation? | Yes | 4 | 4 | 4
| 122 | Are provision for hygenic drinking water available in the labour accomodation? | Yes | 4 | 4 | 4
| 123 | Is atleast one 5 Kg DCP type fire extinguisher located outside every room of the labour accomodation? | Tending to Yes | 4 | 4 | 2
| 124 | Is there a supervisor to look after the labour accomodation? | Yes | 4 | 4 | 4
| 125 | Is the accomodation free from slippery floors and wet surfaces? | Yes | 4 | 4 | 4
| 126 | Is there a separate earthpit for the labour accomodation and is it checked and documented? | Yes | 4 | 4 | 4
| 127 | Is potability of drinking water for the labours tested and documents are maintained? | Yes | 4 | 4 | 4
| 128 | Is the electrical distribution, electrical accessories as per standard and free from damages? | Yes | 4 | 4 | 4
| 129 | Are the toilets / urinals / bathing zones kept clean and tidy in the labour accomodation? | Yes | 4 | 4 | 4
| 130 | Are all the roof and walls of the accomodation free from holes and damages? | Yes | 4 | 4 | 4
| 131 | Are accommodation areas/ rest rooms kept tidy & hygienic with adequate cleanliness? | Yes | 4 | 4 | 4
| 132 | Is a separate kitchen/ cooking area provided at labour accomodation? | Yes | 4 | 4 | 4
| 133 | Is the accomodation free from workers with sleeping arrangements on the floor? | Yes | 4 | 4 | 4
Environment Aspects | 134 | Is water sprinkling done on the ground to control dust? | Yes | 4 | 4 | 4 | 50% | BELOW AVERAGE
| 135 | Is noise level monitoring done and records maintained? | No | 4 | 4 | 0
| 136 | Are adequate means adopted to prevent top soil pollution and ground water pollution? E.g. oil spillage, slurry spillage, concrete debris scattering, etc. | Tending to Yes | 4 | 4 | 2
| 135 | Is the building wrapped to contain dust from neighbouring residential area? |  | NA |  | NA
| 136 | Do all vehicles & equipment with internal combustion (I.C.) engines possess PUC certificates? | Tending to Yes | 4 | 4 | 2
Piling Work | 137 | Is the piling equipment tested and certified by a third party competent person? |  | NA |  | NA | NA | NA
| 138 | Is the approach to the rig free from obstacles? |  | NA |  | NA
| 139 | Is the tank (bentonite / slurry / water) barricaded and safe from all respect? |  | NA |  | NA
| 140 | Is the pile rig inspected periodically and the documents are available? |  | NA |  | NA
| 138 | Is there proper guard of all movable parts of machine? |  | NA |  | NA
| 139 | Are all the accessories and parts of all the pile rig free from damage? |  | NA |  | NA
Excavation and confined space job | 140 | Are there access to all excavated area via ramps or steps or ladders.? Are there hand holds along these? | Tending to Yes | 5 | 5 | 2.5 | 72% | AVERAGE
| 141 | Are excavated area, trenches, pits more than 1.2 meters in depth, provided with hard barricading? | Tending to Yes | 5 | 5 | 2.5
| 142 | Is project free from accumulated water in all the excavated pits? | Yes | 5 | 5 | 3
| 143 | Are there enough cautionary boards "Deep Excavation- Stay Away"? Minimum 10 | Yes | 5 | 5 | 5
| 144 | Is excessive accumulation of load prohobited within 1 meter of the edge of the pit? |  | NA |  | NA
| 145 | Are shoring and struting provided as per technical team recommendation and in good condition? | Yes | 5 | 5 | 5
| 146 | Are confined job works carried out after testing the internal oxygen level and the same is documented? |  | NA |  | NA
| 147 | Is there a set of guidelines on "Confined Space Work" available with the site team and same is followed totally? |  | NA |  | NA
| 148 | Is permit to work being used during confined space work and the same is being documented? |  | NA |  | NA
Hand tools (manual and power driven) | 149 | Are all the moving parts of all machineries gaurded? | Tending to Yes | 4 | 4 | 2 | 87.5% | GOOD
| 150 | Are the emergency stop switches of all the machineries operative? | Tending to Yes | 4 | 4 | 2
| 151 | Are the machineries free from tampered or makeshift appendages? | Yes | 4 | 4 | 4
| 152 | Are all the controls of all the machineries working in good conditions? | Yes | 4 | 4 | 4
| 153 | Is secondary earthing provided for all power driven machines and electrical installations? | Yes | 4 | 4 | 4
| 154 | Are the insulations of all the machineries in good condition? | Yes | 4 | 4 | 4
| 155 | Are the electrical connections of all the machines safely done? | Yes | 4 | 4 | 4
| 156 | Are all the machineries provided with local isolation switch? | Yes | 4 | 4 | 4
Over all Score = |  | 67.03% | E.A.S.E CATEGORY |  |  |  | BELOW AVERAGE
Observation
|  | General Safety | 52.94% | 0
|  | Housekeeping | 45% | 29
|  | Personal Protective Equipment and work apparels | 73.21% | 2
|  | Work at Height | 63.89% | 5
|  | Electrical | 63.89% | 8
|  | Welding, cutting and grinding | 71.43% | 0
|  | Vehicles, Earth movers & Lifting Equipment | 52.27% | 4
|  | Fire Prevention/ Protection | 65.62% | 1
|  | First Aid & Medical Facilities | 83.33% | 0
|  | Welfare Facilities and labour accomodation | 96.43% | 2
|  | Environment Aspects | 50% | 4
|  | Piling Work | NA | 0
|  | Excavation and confined space job | 72% | 1
|  | Hand tools (manual and power driven) | 87.5% | 4
|  |  | Total | 60
|  | Total Count - Partial | 0
|  | Total count - No | 18
|  | Total Deviations | 18
[6 empty] | Yes |  | 90% to 100% |  |  | Considering the bottom score
[6 empty] | Tending to Yes |  | 45% to 90% |  |  |  |  | Score
[6 empty] | Tending to No |  | 10% to 45% |  |  | Yes | 90% to 100% | 100%
[6 empty] | No |  | 0% to 10% |  |  | Tending to Yes | 45% to 90% | 50%
[6 empty] | Assessment Value | Based on organizational maturity and gravity of the activity in the particular project |  |  |  | Tending to No | 10% to 45% | 25%
[6 empty] | NA |  |  |  |  | No | 0% to 10% | 0
1
2
3
4
5
[8 empty] | Good points | Violations | Resolved | Repitition | Jobstoppage notice | HRO
[6 empty] | Yes |  | 8 to 10 | 0 | 90% to 100% | 0 | >5 | 0
[6 empty] | Tending to Yes |  | 4 to 8 | 1 to 10 | 45% to 90% | <20% | 2 to 5 | <20%
[6 empty] | Tending to No |  | 1 to 3 | 10 to 20 | 10% to 45% | >20% | 1 to 2 | >20%
[6 empty] | No |  | 0 | 21 to 30 | 0% to 10% | >40% | 0 | >40%
Anticipated observations
Yes
Tending to Yes
Tending to No
No
Note on D8: Double click inside the cell to activate drop list and select appropriate input. Please do it for the following cells too.

## Graphs
|  | Topic average-All sites |  | Q-4 (24-25) | Q-3 (24-25) | Q-2 (24-25) | Q-1 (25-26)
General Safety | 52.94% | 52.94% | General Safety | 82% | 81% | 79% | 82%
Housekeeping | 45% | 45% | Housekeeping | 84% | 86% | 84% | 86%
Personal Protective Equipment and work apparels | 73.21% | 73.21% | Personal Protective Equipment and work apparels | 79% | 82% | 74% | 78%
Work at Height | 63.89% | 63.89% | Work at Height | 79% | 78% | 76% | 80%
Electrical | 63.89% | 63.89% | Electrical | 87% | 88% | 86% | 86%
Welding, cutting and grinding | 71.43% | 71.43% | Welding, cutting and grinding | 86% | 86% | 84% | 87%
Vehicles, Earth movers & Lifting Equipment | 52.27% | 52.27% | Vehicles, Earth movers & Lifting Equipment | 84% | 85% | 83% | 84%
Fire Prevention/ Protection | 65.62% | 65.62% | Fire Prevention/ Protection | 88% | 89% | 87% | 85%
First Aid & Medical Facilities | 83.33% | 83.33% | First Aid & Medical Facilities | 89% | 86% | 80% | 89%
Welfare Facilities and labour accomodation | 96.43% | 96.43% | Welfare Facilities and labour accomodation | 89% | 88% | 93% | 89%
Environment Aspects | 50% | 50% | Environment Aspects | 88% | 88% | 83% | 85%
Piling Work | NA | #DIV/0! | Piling Work | 0% | 0% | 0% | 75%
Excavation and confined space job | 72% | 72% | Excavation and confined space job | 91% | 100% | 92% | 70%
Hand tools (manual and power driven) | 87.5% | 87.5% | Hand tools (manual and power driven) | 84% | 91% | 91% | 88%
| 67.5% | 67.5%
| 67.03% | 67.03%